## Open points
No. | Open Modules | Status | Timeline | OLD/NEW | Status per IT | Remarks | May 8th | Comments | Owner
1 | Open Savings Account journey | CUG Movement Pending | 2020-06-03 |  | Closed | Not working | 1.Journey not working - does not proceed further 2. Error - temporarily unavailable | Issue is in iOS. | Winjit
2 | Implicit Journey - Mycard to MoBank | CUG Movement Pending | 2020-06-17 | Previously fixed issues - Reopened | Open | 1. I have RBL Bank account - still shows OPEN SAVINGS Account 2. View Savings Acount has open savings account journey, journey does open | I have RBL Bank account - still shows OPEN SAVINGS Account | Working now
3 | Make Payment - RBL Net Banking | Not tested in UAT/CUG | Redirection is done. Final approach to be decided |  | Open | 1. Error - says - you do not have any savings account 2. ios - no action on click | 1. Error - says - you do not have any savings account 2. ios - no action on click | Working now. But intermittently it hangs | Winjit
4 | Fund transfer to RBL bank Account | Not tested in UAT - API not deployed - GL Mapping not done | 2020-05-29 | NEW Delivery | Closed | 1. Validations not built in RBL account number - it is taking wrong account number as well. This is built in other bank details 2. Entered details in RBL Bank tab appear in the Other Bank tab also | Ok
5 | Spend Analyzer | Data wrong for Billing cycle | 2020-05-30 |  | Closed | Ok | Ok
6 | Spend Analyzer - 2 statements clubbed together |  |  |  | Open |  | Open | open | Deferred
7 | Clevertap Notifications - 1. Deep linking not working in Android & ios both 2. Different behaviour for deeplinking on Android and ios 3. All keys for deeplinking not integrated |  | 1 and 2 on 29-May 3rd to be planned after Go-live |  | Closed |  | Deep linking not working in Android | Deep linking not working in Android | Winjit
8 | Earn reward points - Profile Questionnaire | Data not getting saved | Fixed | Previously fixed issues - Reopened | Closed | 1. Data not getting saved 2. screen not proceeding on both CTA's - next & Iill do this later 3. Last CTA does not take you to home page | Previous points solved 1. Can't unselect an option once selected for some questions. Drive preference | closed | closed
9 | Auto Read OTP not working in Android | Observations not fixed | 2020-05-29 |  | Closed | Ok | Ok
10 | Subcription Module | Observations not fixed | 2020-05-29 |  | Closed |  | To be verified
11 | Subcription Module - Active/Inactive Status |  |  |  | Partially open |  | To be verified
12 | Card Settings for P & Q block | Implementation WIP | 2020-05-29 |  | Closed |  | To be verified
13 | Segmented Offers - Validity/Expiry Logic | Validating in CUG today |  |  | Closed |  | Ok
14 | Change in OTP Alert - Registration OTP/Profile Update is only to be sent on SMS and not on Email - Fraud Requirement | Awaiting confirmation |  |  | Closed |  | 1. Profile update - SMS OTP Verbiage does not specify email/Phone 2. OTP for profile update is still being sent to email too, this should only be sent on SMS | Deployment done by Sampath. Smriti to check again | Smriti
15 | Login mPIn - In Registration module , the cursor should automatically move to the 2nd placeholder once the mpin is entered in the first plceholder |  | 2020-05-29 |  | Closed |  | Ok
16 | UBP - Not working - temporarily error |  | Intermittent issue. RCA to be identified |  | Partially open |  |  |  | Winjit
17 | Data does not change once the card is changed from changed card 1. Make Payment screen - The last amount paid and the details like payment mode 2. Rewards 3. Savings & Benefits |  | 2020-05-29 |  | Closed | Ok |  | winjit | Winjit
18 | UPI - This should be As-IS Mycard 1.0 |  | Overlays are not present in VD; so not implemented. Can be taken post go live |  | To be taken post go live
19 | Date format This should be 'Month Date, Year'. Example - May 12, 2020 |  | Drop it for GO LIVE |  | To be taken post go live
20 | Statement download Email and Download both not working showing error - there is no statement available for download |  | statement project observation - will be solved |  | Closed |  | Ok
21 | Payment history - 1. Currently text 'Payment mode' is written in every transcation - drop Payment from verbiage. Only show 'Mode' 2. Payment mode for Cred appears NA - check |  | 2020-05-29 |  | Closed | Ok | Ok
22 | Mismatch of Rewards Data across sections Offers & Rewards Section & My Account section |  | Fixed. Issue came due to delay in running of ETL |  | Closed |  | To be verified
23 | Error on Account Management screen - Missing Api configuration |  |  | Previously fixed issues - Reopened | Closed | API Error | Ok
24 | App Notifications - appear as NOTIFICATIONS in ios |  |  | Previously fixed issues - Reopened | Closed |  | Ok
25 | Videos |  |  | Previously fixed issues - Reopened | Closed | Not viisble in the current build. Screen appears cut | Android - UI/UX issue. To be done like in ios | winjit | Winjit
26 | Customized Statement |  |  |  | Open |  | Not fixed, still showing new tags | deferred | Deferred
27 | Clevertap Push notification Android - 'clicked' & 'viewed'not getting registered ios - 'viewed' not getting registered |  |  |  | Open |  | Still Open | winjit | Winjit
28 | In App notifications - ios - viewed and clicked not capturing in ios |  |  |  | Open |  |  | winjit | Winjit
29 | ios - My account page Screen does not refresh to the top. If you are at the bottom of the page and navigate anywhere in the app, and come back again on Myaccount - it takes you back to the bottom. |  |  |  | Open |  |  | winjit | Winjit
30 | Average spends amount getting cut with spends line - ios |  |  |  | Open |  |  | winjit | Winjit
31 | Profile update section - Photo not getting updated, loader keeps rotating |  |  |  | Open |  |  | manish | Manish
32 | Cloud access pending for photo update |  |  |  | Open |  |  | manish
33 | Profile update - email ID - Basic validations failing in ios , taking without even @ |  |  |  | Open |  |  | winjit | Winjit
34 | International usage - alert SMS/email not coming in ios |  |  |  | Open |  |  | winjit/ sampath | Winjit/ Sampath
35 | Switch off card journey not working in ios |  |  |  | Open |  |  | winjit | Winjit/ Sampath
36 | CMS portal - Offers near you take a lot of time to upload at front end |  |  |  | Open |  |  | winjit | Winjit
| VAS Module - General Observations | Status
1 | Eligiblity not getting refreshed on Real Time Basis | Observation Parked, awaiting confirmation to Re-test | 2020-05-29 |  | Closed | Not getting updated on Real time | Xpress Cash - Ok BT - Ok STPL - not real time
2 | Subscription module not visible for VAS bookings |  | 2020-05-29 |  | Closed |  | To be verified
3 | Subscription Module - Pre closed booking also showing in subcription |  | 2020-06-02 |  | Closed |  | Still showing as ACTIVE on App | sampath | Sampath
4 | Failed transactions also visible in Unbilled as In-Process Transaction with incorrect amount |  | 2020-05-29 |  | Closed | Ok | Ok
5 | Statement dates cases - Front end error on booking. Confirmation message does not show |  | Implementation change at App level. Winjit to come back on date |  | Closed |  | To be verified
6 | Statement Date cases - Confirmation message, verbiage not updated |  |  |  | Closed
7 | Saved Cards details appear again and again - All VAS products |  | 2020-05-29 |  | Closed |  | Does not proceed if saved card is selected | winjit | Winjit
8 | Vision+ Alerts - Awaiting UAT screenshots |  |  |  | Open |  | Not getting alerts | nitika | Vishakha
9 | Loader broken - this was fixed but now again loader is broken, does not let you proceed further for booking |  |  | Previously fixed issues - Reopened | Closed | Broken loader | Ok
XPRESS CASH
1 | Cash Limit reduction to 10% from the default cash limit of 28% - vision+ issue. Raised with FDC | Observation Parked, awaiting confirmation to Re-test |  |  | Closed |  | Ok reflecting at relationship level at vision+
2 | Multiple entries in the Booking file.Booking request initiated twice - but reflects 7 times |  | Implementation change at App level. Winjit to come back on date |  | Closed |  | Operations to confirm
3 | IFSC screen on VAS booking |  |  | Previously fixed issues - Reopened | Closed | Done' CTA not working | Ok
4 | Other bank dropdown shows RBL bank details and these get populated on selecting |  |  |  | NA |  | Open
5 | Description for RBL bank fund transfer is mentioned as ONUS - should be standard for Xpress Cash | [5 empty] | Description for RBL bank fund transfer is mentioned as ONUS - should be standard for Xpress Cash | sampath | Sampath
BALANCE TRANSFER - Error on Booking - Databse Exception
1 | Customer's Account number appended with '000' hence NEFT being Rejected by other Bank | Observation Parked - awaiting confirmation to Re-test |  |  | Closed | Ok | Ok
2 | All cases not being recorded in the VAS Booking file. BT booked from front end but case not recorded in VAS Booking file - Case where NEFT Failed, checked from NEFT records |  | 2020-05-29 |  | Closed |  | Operations to confirm
3 | NEFT Reject cases part of EMI booking file - Increases Operational Manual work |  | Needs to be operationally handled |  | Closed |  | Operations to confirm
4 | Error on Booking - Card not Activated while the card is active |  | Not from App Prespective - check with vision+ team |  | Closed
5 | Other bank credit card field should be masked and re-enter other bank credit card field should be visible - ios issue |  | Already delivered |  | Closed |  | Ok
6 | Error on Booking - No record for given card (appears for customer's booking for first time) Needs to be supressed |  | 2020-05-29 |  | Closed |  | Ok
7 | Change in Description for Transpernpay |  |  |  | Open |  | Open | Transfer n pay | Winjit
8 | Scroll issue on BT booking page |  |  | Previously fixed issues - Reopened | Closed |  | Ok
9 | Database Exception error on booking |  |  | Previously fixed issues - Reopened | Closed |  | Ok
10 | Not able to proceed for booking with Save Card details option | [5 empty] | Does not proceed further | winjit | Winjit
STPL
1 | Solution built only for Transactors | Observation Parked - awaiting confirmation to Re-test | planid reqd in data. 04-Jun |  | Closed
2 | Incorrect Plan booked at backend - 2 columns need to be added in Plan Master to fetch correct Plan |  | 2020-06-04 |  | Closed |  | Ok
3 | Over limit charged on STPL Account |  |  |  | Partially open
4 | Booking file discrepancy - Case appears as failed in booking file, but appears successful in NEFT records |  | 2020-05-29 |  | Closed |  | Operations to confirm
5 | Ashi getting updated without bank details |  | 2020-06-04 |  | Partially open
6 | ROI % for Plans getting round off in DB - to fix character length for this |  | 2020-05-29 |  | Partially open
7 | Error on OTP Page - Database Exception & Invalid Request |  |  |  | Closed
8 | 1. Processing Fee Error on details screen - Previous STPL account is blocked 2. IFSC - not fetching any details per the city and branch |  |  |  | Closed
9 | App Crash happening on STPL screen if decimals are entered |  |  |  | Closed
10 | Incorrect Confirmation message |  |  |  | Open |  | Message verbiage of BT coming for STPL booking | winjit | Winjit
11 | Eligiblity not getting refreshed on Real Time Basis |  |  |  | Open |  | Takes one minute | sampath | Sampath
SNP
1 | Supressing of Debit/Credit entries not relevant to customers | Observation Parked - awaiting confirmation to Re-test | 2020-06-10 |  | Open
2 | Confirmation text verbiage change - Your request has been received. EMI Conversion will happen in the next 24 hours |  |  |  | Open |  | Verbiage change
UI/UX
1 | Wallet Protection | Since this is not going LIVE - front end 'NEW' tag will have to removed |  |  | NA |  | Ok
2 | Sign off - Pivot roots observations on recent build |  |  |  | Open

## VAS bookings May 8th
| Xpress Cash - Outside RBL | Xpress Cash - RBL Bank | BT | STPL
Reema | 25000 | 10000 | 5000
Smriti |  |  |  | 20000
Kaamil

## Customized Statement
Statement Tags |  | As per vision+ changes
Last bill amount | New to be added post statement project is LIVE
Payment & Credits | Old - As-Is in CS | Payments credit + transferred to EMI
New Purchases | Old -New Debits - As-Is in CS | New Purchases + fees and charges
Transferred to Emi | New to be added post statement project is LIVE
Monthly Debit Emi | Old - As-Is in CS
Fees & charges | New to be added post statement project is LIVE
GOOD & Services Tax | Old - As-Is in CS
Statement Date | Old - As-Is in CS

## Alerts status (hidden)
Product Name | RBL | BFL
STPL – Booking | Ok | Share again
STPL – OTP SMS | Ok | Ok
STPL – OTP Email | Ok | Ok
BT – Booking | To be shared | Share again
BT – OTP SMS | To be shared | Share again
BT – OTP Email | To be shared | Share again
XC – Booking | To be shared | To be shared
XC – OTP SMS | To be shared | To be shared
XC – OTP Email | To be shared | To be shared