## Phase 2 -Priority UAT Timeline
No. | Modules | Priority | Priority | Comments | Dev Status ( Winjit) | Delivery Date | Dev Comments ( Winjit) | VD status | VD's | MOM as of April 21st | MOM as of Jun 03, 2020
1 | Mycard to Mobank - SSO | Sprint 1 | June 19th
2 | URL for Mycard which open's up the App and not Play store | Part of GO LIVE | BUG | Asif to provide timeline |  | 2020-04-29 |  |  |  | To be delivered in UAT on 29th April | in 15th june go -live
3 | Add on security for New Registration process | Part of GO LIVE | Dropped | Asif to provide documentation for creating journey | [6 empty] | NA
4 | UPI - This should be As-IS Mycard 1.0 | Sprint 1 | BUG
5 | Date format This should be 'Month Date, Year'. Example - May 12, 2020 | Sprint 1 | Not sticky
6 | Push notification - pending Deep linking | Sprint 1 | Sprint 1
7 | Wallet Protection (W/O Renewal) | Sprint 1 | Sprint 1
8 | Exclusive benefits to be linked to Card benefits. To give View More Option | Sprint 1 | Sprint 1
9 | Profile update - Add one more placeholders for mobile and email | Sprint 1 | Sprint 1
10 | Document upload - should have an option for clicking a picture and submitting document Document Size to increase |  | Sprint 1 | IT team to check
11 | EMI Protect | Sprint 1 | Sprint 1 | discussion on 16h june for journey walkthrough
12 | Change card option - 1. Exclusive Facilities Page 2. Card Benefits | Sprint 1 | Sprint 1
13 | Manage Card settings per RBI guidelines | Sprint 1 | Sprint 1 | VD updates in progress |  |  | NA | First Draft ready | https://xd.adobe.com/view/d30ff19f-5cc9-4e8c-5b74-738cfb2e4551-a53e/screen/9958f300-c901-4ea6-8d38-59dff8ea27cc/Splash-411/ |  | Business to provide final VD
14 | STPL card account | Sprint 1 | Sprint 1 | VD links given, Awaiting timeline |  |  |  | VD links given | https://xd.adobe.com/view/6fa5e495-5433-47fc-76d4-6b2d90a623b9-1994/screen/6fcb2a93-b372-412b-878a-de875a5fd95c/Home-option-2-6?fullscreen | Timelines awaited by tomorrow April 22nd | Designs completed, intgration pending - Manish to update
15 | Scan & Pay with AGS | Sprint 1 | Sprint 1 | Manish to initiate the discussion and update on Monday | Awaiting Details |  | Need final solution document and implementation approach | Available in VD |  | Call with Master card - Manish will update. Manish to update timeline by Friday April 24th | Manish to update
16 | Third Party Integrations- Vouchagram for experience & vouchers | Sprint 1 | Sprint 1 | Integration with Vouchgram done. Payment page flow WIP | WIP | 2020-04-17 |  | PWA approach , URL ready |  | UAT- 29th April | UAT timeline to be shared
17 | EMI infinity pass | Sprint 1 | Sprint 1 | Manish to initiate the discussion and update on Monday | Awaiting Details |  | Need final solution document and implementation approach | Available in VD |  | 11th May will be receving API from sampath and also we are checking the dependency for current process post that will abe to give UAT timelines - Awaited End delivery Timelines by Friday April 24th | Manish to update
18 | Earn reward points Migration of existing database - Reward points credit to customers | Sprint 1 | Sprint 1 | Vishakha to update on the project plan for this | NA | NA | NA | NA |  | Same as point 24 - Business to decide on a cut off date | Business to update
19 | CMS - 3 level hierarchy for Offer Approvals
20 | To show 4 digit PIN in the app post OTP validation. |  | Sprint 1
21 | Acquisition Module - New Card acquisition | Sprint 1 |  | Internal meeting - business team with IT | Awaiting Details |  | Need final solution document and implementation approach | Wireframes available, to be reviewd with Product team today | https://xd.adobe.com/view/0426855d-39ef-486e-52f2-84bce26bcfad-7217/screen/289a5e1d-e41e-4a29-b984-1dcca9c6c694/Login-First-Time-User-1
22 | Track your Card - Post login | Sprint 2 | Sprint 2 | Sampath to check on API | Awaiting Details |  | Need final solution document and implementation approach
23 | UBP - New UI/UX | Sprint 1 | Sprint 2 | Feedback on UI/UX shared | Awaiting Details |  | Need list of featured and UI as discussed with business on call | Business team to discuss
24 | Offers - CMS portal for Merchant/Aggregators | Part of GO LIVE | Sprint 2 | IT team to check | WIP | 2020-04-10 |  | NA |  |  | Business sign-off pending
25 | App should have a search Option for Offers & Rewards section | Sprint 1 | Sprint 2
26 | Offers at store should have a Store Locator, this should et directed to google maps
27 | Customizable card - Card Benefit section | Sprint 1 | Sprint 2 | Approach discussed with Winjit
28 | Upgrade Module - API changes | Sprint 1 | Sprint 2 | Pending from Business - Mudasir | Awaiting Details |  | Waiting for inputs and api changes |  |  | Timelines awaited by tomorrow April 22nd | Manish to update
29 | First time login journey - including ‘change your PIN’, ‘getting started’ | Sprint 1 | Sprint 2 | VD's created, pending for Business Approval | Awaiting Details |  | Waiting for VD | Wireframes Available - Currently has 3 options 1. Set card pin 2. profile update 3. Track your card. Should manage card setting sbe added | https://xd.adobe.com/view/058ee025-f8c1-4ae7-4ce4-8a51aae27341-73bf/screen/0aeb1b91-588b-46b1-9fa5-d71b580e1ffe/Splash-342/?mv=product&mv2=accc | 1. 1st & 2nd - 29th April UAT 2. Mudasir and team is working on this, VD finalised need to be done . Sharddha will able to confirm. Timelines awaited by Friday April 24th | Screens - ready, awaiting update on API Tags - Manish to update Business to share approach note
30 | Payments - E-Mandate | Sprint 1 | To be discussed | Tech discussion done with Razorpay team. API details received from RP. | Awaiting Details |  | Need final solution document and implementation approach | NA - BRD submitted (To be done for Website & Mycard both) |  | Ankita has provided 5th June UAT , will start implementing parallelly with Winjit team UAT 10th June - Ashish to update timeline for Mycard delivery by Friday April 24th | Manish to update
31 | Third Party Integrations- Term Insurance - HDFC | Sprint 1 | Sprint 3 | Awaiting update on Plan from IT Team - Call to be scheduled on Friday | Awaiting Details |  | Need final solution document and ESB api's | 1. PWA Approach 2. Requested URL from HDFC |  | Will able to provide the Solution approach in next week post discussion with HDFC team( Thursday we have set up a call with team) require url for PWA approach - Timelines awaited by Friday April 24th | Awaiting response from HDFC team
32 | Third Party Integrations- Health Insurance - Religare | Sprint 1 | Sprint 2 | Delivered on UAT. UAT build yet to be received from IT Team | Delivered on UAT | 2020-04-04 |  | VD Available - but needs minor updated | https://xd.adobe.com/view/058ee025-f8c1-4ae7-4ce4-8a51aae27341-73bf/screen/b011bb36-e89b-4026-bb01-536cb06dba0c/Splash-267 | UAT delivered | API integration pending - Manish to update
33 | Third Party Integrations- Personal/Accident Insurance | Sprint 1 | Sprint 2 | Delivered on UAT. UAT build yet to be received from IT Team | Delivered on UAT | 2020-04-04 |  | VD Available - but needs minor updated |  | UAT delivered | API integration pending - Manish to update
34 | Third Party Integrations- Travel Insurance | Sprint 1 | Sprint 2 | VD's WIP from Buisness | WIP |  |  | VD Available - but needs minor updated |  | UAT- 29th April | UAT timeline to be shared
35 | Third Party Integrations- Extended warranty - One Assist | Sprint 1 | Sprint 3 | Asif to update on UAT timeline - Monday | WIP |  |  | VD is complete |  | UAT- 29th April | Business to update
36 | Rate the app - should be available even after rating the app once.currently it says you have already done | Sprint 1 | Sprint 3
37 | Apply for Add - on Card | Sprint 1 | Sprint 3 | VD links given, Awaiting timeline |  |  | VD's final, given to IT Team |  | https://xd.adobe.com/view/be12539c-6b40-4bfc-650a-3250788527e0-c823/ | 1. No integratation with CRM 2. UAT 7th May | Manish to update
38 | Add on card should not see primary card details | Sprint 1 | Sprint 3 | Awaiting update from Sampath | Awaiting Details |  | Need final solution document and implementation approach. What all is to be changed | NA |  | 1. Need to confirmation from Business for Final details for Addon card will be the same which has been shared by Reema earlier. 2. Shraddha to provide the timelines on approach, Solution date will provide by shraddha, parallely we are checking any related queries with winjit team, will come with comprehensive date for UAT, what check and control will required, will able to update UAT date with all this final solution - Timelines awaited by Friday April 24th | Manish to update
39 | Post login - Credit cards Payments with RBL net banking - Implicit journey | Sprint 1 | Sprint 3 | VD links given, Awaiting timeline |  |  | Need to discus with ESB and internal teams for implementation approach | VD's final, given to IT Team | https://xd.adobe.com/view/6fa5e495-5433-47fc-76d4-6b2d90a623b9-1994/screen/6fcb2a93-b372-412b-878a-de875a5fd95c/Home-option-2-6?fullscreen | UAT-15th May | Part of Phase 1 tracker
40 | Chatbot SSO | Sprint 1 | Sprint 3 | Solution document sent by Winjit team to respective Stakeholders | WIP |  | Discussion on SS approach intiated | NA |  | UAT-20th May - to update tomorrow | Manish to update
41 | IFT - RBL Account number should be auto populated |  | Sprint 4
42 | Compare Cards journey | Sprint 1 | Sprint 4 | Pending from Business - Mudasir | Awaiting Details |  | Need solution and VD | No VD- Journey solutioning WIP |  | Work was done in CMS portal, Winjit team has highlighted the discrepency , so new approach required can take take up for solution & timelines(Pending at Mudasir) | Business to share final VD
43 | Redeem Rewards SSO | Sprint 1 | Sprint 4 | Manish to initiate the discussion and update on Monday | Awaiting Details |  | Need final solution document and implementation approach | NA |  | Shraddha has initiated a mail for solution approach to Kavya,will update on UAT date once the confirmation received by this week - Ashish to update by Friday April 24th | Manish to update
44 | My account - Exclusive offers | Sprint 1 | Redirect to Offers section | Asif to update timeline | WIP | 2020-04-15 |  | VD Available |  | UAT-7th May | UAT timline to be shared
45 | Banners between View Transactions | Sprint 1 |  | Shraddha to update on a single API for VAS eligiblity check | Awaiting Details |  | Need single eligbility check api for all VAS products | Available in VD |  | Supriyo to provide the details for single api , Ashish has drop a mail to Supriyo for creating an VIEW of all offer in VAS Will able to provide the UAT dates as we received postive confirmation frm supriyo 25th May UAT - Ashish to confirm on Friday April 24th | Manish to update
46 | Open Savings Account Native Journey (additional fields) - Discussion needed with Ulka and team | Sprint 2 |  | Business to update | Awaiting Details |  | Need final solution document and implementation approach | Check with Dinesh
47 | Third party Integration - Dineout for dinning | Sprint 2 |  |  | Awaiting Details |  | Need final solution document and implementation approach | PWA Approach
48 | Third party Integration - Integration with Nearby | Sprint 2 |  |  | Awaiting Details |  | Need final solution document and implementation approach | PWA Approach
49 | Third party Integration - Integration with OYO | Sprint 2 |  |  | Awaiting Details |  | Need final solution document and implementation approach | PWA Approach
50 | Third party Integration - Integration with MMTC Digital Gold | Sprint 2 |  |  | Awaiting Details |  | Need final solution document and implementation approach | PWA Approach
51 | Refer Now section | Sprint 1 |  | VD in progress | Awaiting Details |  | Need final solution document and implementation approach | Journey WIP
52 | Reminder section | Sprint 2 |  | Customer should be abe to set any reminder in this section including UBP reminders | Awaiting Details |  | Need final solution document and implementation approach | Business team to discuss on Approach
53 | Service Request section - History of SR's Open/Closed | Sprint 2 |  |  | Awaiting Details |  | Need final solution document and implementation approach | Available in VD
54 | Service Request section - Fetching of SRs & Reverse feed of SRs (CRM Integration) | Sprint 2 |  |  | Awaiting Details |  | Need final solution document and implementation approach | NA
55 | Chatbot - Deeplink within Chatbot to Internal modules | Sprint 2 |  |  | Awaiting Details |  | Need final solution document and implementation approach | NA
56 | Track your application - Pre login | Sprint 1 |  |  | Awaiting Details |  | Need final solution document and implementation approach | VD's available , but needs to be updated | https://xd.adobe.com/view/058ee025-f8c1-4ae7-4ce4-8a51aae27341-73bf/screen/0aeb1b91-588b-46b1-9fa5-d71b580e1ffe/Splash-342?mv=product&mv2=accc
57 | Corporate Cards should be able to login to MyCard app as well. They should only be able to see – statement, transactions and make payment options. Rest all options(including offers/rewards/exclusive facilities/service request/card settings etc. – need to be disabled for corporate cards) | Sprint 3 |  |  | Awaiting Details |  | Need final solution document and implementation approach | Business team to discuss
58 | PayU Payment Channel | Sprint 3 |  |  | Awaiting Details |  | Need final solution document and implementation approach | NA
59 | New Payment Journey - Switch at backend for Monitoring PG, Enabling PG basis performance. New Payment Journey where customer should not be shown PGs , should only be shown the payment mode i.e. Netbanking, Debit Card, UPI, Emandate | Sprint 3 |  |  | WIP |  | Implementation approach is finalised. Will share solution document with team by 1/4/2020 | VD not availabe
60 | Third Party Integrtaion - Grocery | Sprint 3 |  |  | Awaiting Details |  | Need final solution document and implementation approach | Business team to discuss on Approach
61 | Gift A Card | Sprint 3 |  |  | Awaiting Details |  | Need final solution document and implementation approach | Business team to discuss on Approach
62 | CMS Portal - Cashback and Coupon Module | Sprint 3 |  |  | Awaiting Details |  | Need final solution document and implementation approach | To be discusse with teams
63 | Rewards Portal - development | Sprint 3 Out of Scope for Mycard 2.0 |  | Journey will be PWA - Easy rewards Portal to be developed per Mycard 2.0 guidelines | NA |  | Need final solution document and implementation approach | NA
64 | Bonus reward icon - Accelerated Reward Points on a daily basis |  |  | To check with Supriyo Sir for Implementation | NA |  | Need final solution document and implementation approach | NA
65 | Third Party Integrations- Cleartrip integration for flight, hotel & Activities | Sprint 3 |  | Last Priority Business to discuss approach and confirm | Awaiting Details |  | Final approach to be taken. PWA or API integration | Wireframe available for Hotel and Flight | Hotel - https://xd.adobe.com/view/19d1b33f-75eb-4e77-4b86-6117972b9013-6fe0/ Flights - https://xd.adobe.com/view/1335515c-ad08-4700-6c2a-cd0d7d48121b-6504/screen/f6b0245f-a03b-48cb-af5c-d4191d233e52/Search-Flight-15/
66 | Earn reward points Removal of profile update scetion from Rewards portal | For Internal Tracking |  |  | NA | NA | NA | NA |  | Same as point 24 - Business to decide on a cut off date | Business to update

## Plan from IT
CR Name | % Work done on APK | % Work done on ESB | % Work done on DW and other systems | % Work done on Testing | Sprint
Wallet Protection (W/O Renewal) | 100% | 90% | 90% | 90% | 1 | Take up seretate OneQ for Renewal
Vouchagram for experience & vouchers | 90% | 90% | 50% | 0% | 1
Religare - Health Insurance - Religare | 90% | 50% | 0% | 0% | 2
Religare - Personal/Accident Insurance | 90% | 50% | 0% | 0% | 2
Religare - Travel Insurance | 90% | 50% | 0% | 0% | 2
Extended warranty - One Assist | 50% | 50% | 50% | 0% | 3
Upgrade your card | 100% | 70% | 70% | 0% | 2
Term Insurance - HDFC | 10% | 0% | 0% | 0% |  | To be discussed
Payments - E-Mandate | 0% | 30% | 0% | 0% |  | To be discussed
EMI Protect | 0% | 0% | 0% | 0% | 1
Chatbot SSO | 0% | 0% | 0% | 0% | 3

## Phase 2 - Priority (hidden)
No. | Modules | Priority | Comments | Status | VD status | VD's
1 | Offers - CMS portal for Merchant/Aggregators |  | To be delivered by Mid April |  | NA
2 | UBP Module - Cross button to enable one time logout from the module |  | Asif to update on feasibility |  | NA
3 | New customized statement layout |  |  |  | Available in VD
4 | Manage Card settings per RBI guidelines |  | FDC development (API) WIP - to check once this is developed |  | First Draft ready | https://xd.adobe.com/view/d30ff19f-5cc9-4e8c-5b74-738cfb2e4551-a53e/screen/9958f300-c901-4ea6-8d38-59dff8ea27cc/Splash-411/
5 | Upgrade Module - API changes | Before GO LIVE | Detailed BRD needed from Mudasir, call setup with all teams for discussion
6 | Compare Cards journey | Sprint 1 | Detailed BRD needed from Mudasir, call setup with all teams for discussion |  | No VD- Journey solutioning WIP
7 | Mycard to Mobank - SSO | Sprint 1 | Development done - awaiting UAT |  | NA
8 | First time login journey - including ‘change your PIN’, ‘getting started’ | Sprint 1 | Business to provide wireframes |  | Wireframes Available - Currently has 3 options 1. Set card pin 2. profile update 3. Track your card. Should manage card setting sbe added | https://xd.adobe.com/view/058ee025-f8c1-4ae7-4ce4-8a51aae27341-73bf/screen/0aeb1b91-588b-46b1-9fa5-d71b580e1ffe/Splash-342/?mv=product&mv2=accc
9 | Apply for Add - on Card | Sprint 1 |  |  | check with Dinesh
10 | Add on card should not see primary card details | Sprint 1 | Sampath to update |  | NA
11 | Scan & Pay with AGS | Sprint 1 | To check with AB |  | Available in VD
12 | Post login - Credit cards Payments with RBL net banking - Implicit journey | Sprint 1 | Business to provide journey |  | VD not available
13 | Payments - E-Mandate | Sprint 1 | Schedule call with Ankita & Channel Team for a debrief |  | NA - BRD submitted (To be done for Website & Mycard both)
14 | Third Party Integrations- Term Insurance - HDFC | Sprint 1 | Asif to update on UAT timeline - Wednesday |  | 1. PWA Approach 2. Requested URL from HDFC
15 | Third Party Integrations- Health Insurance - Religare | Sprint 1 | Asif to update on UAT timeline - Monday |  | VD Available - but needs minor updated | https://xd.adobe.com/view/058ee025-f8c1-4ae7-4ce4-8a51aae27341-73bf/screen/b011bb36-e89b-4026-bb01-536cb06dba0c/Splash-267
16 | Third Party Integrations- Personal/Accident Insurance | Sprint 1 | Asif to update on UAT timeline - Monday |  | VD Available - but needs minor updated
17 | Third Party Integrations- Travel Insurance | Sprint 1 | Asif to update on UAT timeline - Monday |  | VD Available - but needs minor updated
18 | Third Party Integrations- Extended warranty - One Assist | Sprint 1 | Asif to update on UAT timeline - Monday |  | VD is complete
19 | Third Party Integrations- Vouchagram for experience & vouchers | Sprint 1 | Asif to update on UAT timeline - Monday |  | PWA approach , URL ready
20 | Third Party Integrations- EMI infinity pass | Sprint 1 | Asif to update on UAT timeline - Monday |  | Available in VD
21 | Redeem Rewards SSO | Sprint 1 |  |  | NA
22 | App notification ( Clevertap + UBP ) - PUSH notifications + Deeplink Rich media notifications | Sprint 1 | Asif to update on UAT timeline - Monday |  | NA
23 | Earn reward points Removal of profile update scetion from Rewards portal | Sprint 1 |  |  | NA
24 | Earn reward points Migration of existing database - Reward points credit to customers | Sprint 1 |  |  | NA
25 | My account - Exclusive offers | Sprint 1 |  |  | VD Available
26 | Chatbot SSO | Sprint 1 |  |  | NA
27 | Banners between View Transactions | Sprint 1 |  |  | Available in VD
28 | Open Savings Account Native Journey (additional fields) - Discussion needed with Ulka and team | Sprint 2 | Business |  | Check with Dinesh
29 | Third party Integration - Dineout for dinning | Sprint 2 |  |  | PWA Approach
30 | Third party Integration - Integration with Nearby | Sprint 2 |  |  | PWA Approach
31 | Third party Integration - Integration with OYO | Sprint 2 |  |  | PWA Approach
32 | Third party Integration - Integration with MMTC Digital Gold | Sprint 2 |  |  | PWA Approach
33 | Refer Now section | Sprint 2 |  |  | Journey WIP
34 | Reminder section | Sprint 2 | Customer should be abe to set any reminder in this section including UBP reminders |  | Business team to discuss on Approach
35 | Service Request section - History of SR's Open/Closed | Sprint 2 |  |  | Available in VD
36 | Service Request section - Fetching of SRs & Reverse feed of SRs (CRM Integration) | Sprint 2 |  |  | NA
37 | Chatbot - Deeplink within Chatbot to Internal modules | Sprint 2 |  |  | NA
38 | Acquisition Module - New Card acquisition | Sprint 2 |  |  | Wireframes available, to be reviewd with Product team today | https://xd.adobe.com/view/0426855d-39ef-486e-52f2-84bce26bcfad-7217/screen/289a5e1d-e41e-4a29-b984-1dcca9c6c694/Login-First-Time-User-1
39 | Track your application - Pre login | Sprint 2 |  |  | VD's available , but needs to be updated | https://xd.adobe.com/view/058ee025-f8c1-4ae7-4ce4-8a51aae27341-73bf/screen/0aeb1b91-588b-46b1-9fa5-d71b580e1ffe/Splash-342?mv=product&mv2=accc
40 | Track your Card - Post login | Sprint 2
41 | UBP Journey on Mobank App - Mapping with Mycard 1.0 Journey - Business Team | Sprint 2 | To be discussed with Winjit Team |  | Business team to discuss
42 | Corporate Cards should be able to login to MyCard app as well. They should only be able to see – statement, transactions and make payment options. Rest all options(including offers/rewards/exclusive facilities/service request/card settings etc. – need to be disabled for corporate cards) | Sprint 3 |  |  | Business team to discuss
43 | PayU Payment Channel | Sprint 3 |  |  | NA
44 | New Payment Journey - Switch at backend for Monitoring PG, Enabling PG basis performance. New Payment Journey where customer should not be shown PGs , should only be shown the payment mode i.e. Netbanking, Debit Card, UPI, Emandate | Sprint 3 |  |  | VD not availabe
45 | Third Party Integrtaion - Grocery | Sprint 3 |  |  | Business team to discuss on Approach
46 | Gift A Card | Sprint 3 |  |  | Business team to discuss on Approach
47 | CMS Portal - Cashback and Coupon Module | Sprint 3 |  |  | To be discusse with teams
48 | Rewards Portal - development | Sprint 3 Out of Scope for Mycard 2.0 | Journey will be PWA - Easy rewards Portal to be developed per Mycard 2.0 guidelines |  | NA
49 | Bonus reward icon - Accelerated Reward Points on a daily basis |  | To check with Supriyo Sir for Implementation |  | NA
50 | Third Party Integrations- Cleartrip integration for flight, hotel & Activities | Sprint 3 | Asif to update on UAT timeline - Wednesday |  | Wireframe available for Hotel and Flight | Hotel - https://xd.adobe.com/view/19d1b33f-75eb-4e77-4b86-6117972b9013-6fe0/ Flights - https://xd.adobe.com/view/1335515c-ad08-4700-6c2a-cd0d7d48121b-6504/screen/f6b0245f-a03b-48cb-af5c-d4191d233e52/Search-Flight-15/

## MOM as of Mar 30th (hidden)
No. | Module | Comment
1 | Real time NEFT status and Failure reason to be stamped in ASHI and ESB Audit table | 1. Previous day cases for NEFT failure - Operations to check files and process NEFT Reject cases if required and update ASHI (real time) with details 2. Real time ASHI update by operations - Shraddha/Ashish to confirm 3. UTR number to be added in the SMS - Smriti
2 | NEFT failure reversal to be auto posted | No other solutioning required Failure cases to be posted by Operations
3 | Offline booking process should use real time OTB | No other solutioning required
4 | Reversed Offline booking to update eligible amount real time for another booking | No other solutioning required Shraddha to confirm on eligiblity being updated real time across channels
5 | Offline Ops process to be replicated for online cases a) reverse feed in table b) MIS/ report c) query job | No other solutioning required
6 | Status for Preclosed/cancelled plans in subscription table | No other solutioning required Sapna to update on Status
7 | Membership fee for Upgraded card to be parametrized | To be discussed in Upgrade call
8 | Onus reversal for technical failure/timeout cases | No other solutioning required End of day Recon for now. Checkout for timeout cases and build post this
9 | Auto Onus debit for partners which do not have SI triggering mechanism like Billdesk | Renewal API not available with Partner. IT team to solution internally
10 | E-Mandate project delivery timelines | To schedule a walkthrough with IT team
11 | New Pricing to be dynamically handled for Insurance module | Discussed, To be solutioned for Third Party Modules