## Customized Statement
Statement Tags |  | As per vision+ changes
Last bill amount | New to be added post statement project is LIVE
Payment & Credits | Old - As-Is in CS | Payments credit + transferred to EMI
New Purchases | Old -New Debits - As-Is in CS | New Purchases + fees and charges
Transferred to Emi | New to be added post statement project is LIVE
Monthly Debit Emi | Old - As-Is in CS
Fees & charges | New to be added post statement project is LIVE
GOOD & Services Tax | Old - As-Is in CS
Statement Date | Old - As-Is in CS

## Alerts status (hidden)
Product Name | RBL | BFL
STPL – Booking | Ok | Share again
STPL – OTP SMS | Ok | Ok
STPL – OTP Email | Ok | Ok
BT – Booking | To be shared | Share again
BT – OTP SMS | To be shared | Share again
BT – OTP Email | To be shared | Share again
XC – Booking | To be shared | To be shared
XC – OTP SMS | To be shared | To be shared
XC – OTP Email | To be shared | To be shared

## Open points
No. | Open Module - Other Than VAS | Status | Timeline | OLD/NEW ISSUE | Fixed/Not Fixed | Remarks-Business | Winjit_comments_2ndJune | Testing team Comments_03rd_June | TSG comments_3rd June | Status | SPOC
1 | Open Savings Account journey | CUG Movement Pending | 2020-06-03 |  | DIY working as expected. Button name is displayed based on flag received from API response. Winjit - Other Observations shared with us today morning. | Not working | Fixed Intermittent API side issue reported to API team | Fail getting error as "Due to technical issue…"after entering mobile no and clicking on submit button | To be checked on CUG | Open |  | BUSNISS SIGNOFF | CLOSED
2 | Implicit Journey - Mycard to MoBank | CUG Movement Pending | 2020-06-17 | Previously fixed issues - Reopened | NA | 1. I have RBL Bank account - still shows OPEN SAVINGS Account 2. View Savings Acount has open savings account journey, journey does open |  |  | MoBank ESB to fix the issue | Open | Winjit/Manish/Vishakha | IN UAT | WIP
3 | Make Payment - RBL Net Banking | Not tested in UAT/CUG | Redirection is done. Final approach to be decided |  | Winjit - Fixed - Redirected to Mobank Discussion/Clarity pending for complete solution | 1. Error - says - you do not have any savings account 2. ios - no action on click | Fixed | Fail When user clicks on Rbl net banking navigate to Mobank Playstore | To be checked on CUG | Open |  |  | OPEN
4 | Fund transfer to RBL bank Account | Not tested in UAT - API not deployed - GL Mapping not done | 2020-05-29 | NEW Delivery | Fixed | 1. Validations not built in RBL account number - it is taking wrong account number as well. This is built in other bank details 2. Entered details in RBL Bank tab appear in the Other Bank tab also | 1. NA 2. Fixed | Fail, Error as "We apologize…" on otp screen | IFT issue to be check by Winjit Team | Open | Winjit | spoc
5 | Spend Analyzer | Data wrong for Billing cycle | 2020-05-30 |  | Fixed | Ok |  |  | Signoff received from Business | Closed
6 | Spend Analyzer | 2 statements clubbed together |  |  | OPEN NA - Appside |  |  |  | Need to discuss with business or need to take a call | Open | Manish/Vishakha
7 | Clevertap Notifications | 1. Deep linking not working in Android 2. Different behaviour for deeplinking on Android and ios 3. All keys for deeplinking not integrated | 1 and 2 on 29-May 3rd to be planned after Go-live |  | 1. Android deeplinking working. Device specific issue - One Plus 5T 2. Fixed 3. New keys not to be taken for Go Live; will be taken post Go Live |  | 1. Android deeplinking working. Device specific issue - One Plus 5T 2. Fixed 3. New keys not to be taken for Go Live; will be taken post Go Live | Clevertap portal was not working …temp unavailable | Testing team - Push notification - Pass In App notification - not getting in app notification 3rd point to be taken Post Go Live | Open | Winjit
8 | Earn reward points - Profile Questionnaire | Data not getting saved | Fixed | Previously fixed issues - Reopened | API side issue | 1. Data not getting saved 2. screen not proceeding on both CTA's - next & Iill do this later 3. Last CTA does not take you to home page | 1. API side issue 2. Fixed 3. Fixed | Pass | 1. Fixed 2. Need to do a CUG testing | Closed/Open | Manish/Vishakha
9 | Auto Read OTP not working in Android | Observations not fixed | 2020-05-29 |  | Fixed | Ok |  |  | Signoff received from Business | Closed
10 | Subcription Module | Observations not fixed | 2020-05-29 |  | Fixed |  | Fixed | TBD | Sapna to run the etls for subcription module | Closed
11 | Subcription Module - Active/Inactive Status | [5 empty] | Fixed ; checked on Smritis card | TBD | 1. BT, xpress cash pending(health, emi details testing done from Winjit team) 2. End date tag provided | Open | Winjit
12 | Card Settings for P & Q block | Implementation WIP | 2020-05-29 |  | Fixed - But not tested |  | Fixed - But not tested | Data dependency - Sent mail | Testing is pending from winjit& RBL | Open | Abhinav/Winjit
13 | Segmented Offers - Validity/Expiry Logic | Validating in CUG today |  |  | Fixed |  | Fixed | Pass | Fixed | Closed
14 | Change in OTP Alert - Registration OTP/Profile Update is only to be sent on SMS and not on Email - Fraud Requirement | Awaiting confirmation |  |  | NA |  |  |  | Sampath | Open | Sampath
15 | Login mPIn - In Registration module , the cursor should automatically move to the 2nd placeholder once the mpin is entered in the first plceholder |  | 2020-05-29 |  | Fixed |  | Fixed | Pass | Fixed | Closed
16 | UBP - Not working - temporarily error |  | Intermittent issue. RCA to be identified |  | Not Fixed Intermittent issue |  | Intermittent issue. RCA not yet identified | Still giving temporarily error | Intermittent issue | Open | Winjit
17 | Make Payment screen - The last amount paid and the details like payment mode do not change once the card is changed from changed card |  | 2020-05-29 |  | Fixed | Ok |  |  | Signoff received from Business | Closed
18 | UPI - This should be As-IS Mycard 1.0 |  | Overlays are not present in VD; so not implemented. Can be taken post go live | [5 empty] | post go live (closed) | NA
19 | Date format This should be 'Month Date, Year'. Example - May 12, 2020 |  | Drop it for GO LIVE |  | To be taken post go live |  |  |  | post go live (closed) | NA
20 | Statement download Email and Download both not working showing error - there is no statement available for download |  | statement project observation - will be solved |  | Fixed |  |  |  | Fixed | Closed
21 | Payment history - 1. Currently text 'Payment mode' is written in every transcation - drop Payment from verbiage. Only show 'Mode' 2. Payment mode for Cred appears NA - check |  | 2020-05-29 |  | Fixed | Ok |  |  | Signoff received from Business | Closed
22 | Mismatch of Rewards Data across sections Offers & Rewards Section & My Account section |  | Fixed. Issue came due to delay in running of ETL |  | NA |  |  |  | Fixed | Closed
23 | Error on Account Management screen - Missing Api configuration |  |  | Previously fixed issues - Reopened |  | API Error | Fixed | Fail - On click of My Account screen getting error "Something went wrong…" | Fixed in CUG, error occurs in UAT due to deployment pending | Closed/Open | Winjit/Vishakha
24 | App Notifications - appear as NOTIFICATIONS in ios |  |  | Previously fixed issues - Reopened |  |  | Fixed | Currently don't have iOS device | Fixed(Not able to check on iOS ) | Open | Abhinav
25 | Videos |  |  | Previously fixed issues - Reopened | Videos not visible | Not viisble in the current build. Screen appears cut | Fixed | Fail -Videos are missing in UAT | Need to check in CUG | Open | Winjit
26 | Customized Statement |  |  |  | New tags should not come on the app front end till the Customized Statement is LIVE |  | TBD - Asif and Sampath |  | Need to take a call with AB | Open
| VAS Module - General Observations | Status
1 | Eligiblity not getting refreshed on Real Time Basis | Observation Parked, awaiting confirmation to Re-test | 2020-05-29 |  | NA | Not getting updated on Real time |  |  | WIP | Open | Sampath
2 | Subscription module not visible for VAS bookings |  | 2020-05-29 |  | NA |  |  |  | as is point no 10- Need to test in CUG | Open | Sapna
3 | Subscription Module - Pre closed booking also showing in subcription |  | 2020-06-02 |  | NA |  |  |  | Business to check | Closed
4 | Failed transactions also visible in Unbilled as In-Process Transaction with incorrect amount |  | 2020-05-29 |  | Fixed | Ok |  |  | Signoff received from Business | Closed
5 | Statement dates cases - Front end error on booking. Confirmation message does not show |  | Implementation change at App level. Winjit to come back on date |  | Not Fixed - This is not an issue . Number of times user clicks on button a request will be initiated. We do not have freeze screen implemented anywhere in the app . Loader is cancellable , once it is cancelled new request is initiated |  | Fixed - We have disabled Submit button till response comes for 1 API call Let us know if issue still persists | Pass | Fixed | Closed
6 | Statement Date cases - Confirmation message, verbiage not updated |  |  |  | Fixed |  | Fixed - We have disabled Submit button till response comes for 1 API call Let us know if issue still persists | Pass | Fixed | Closed
7 | Saved Cards details appear again and again - All VAS products |  | 2020-05-29 |  | Fixed |  | Not Fixed - TBD Sampath |  | Winjit to fix(suppressed issue) | Open | Winjit
8 | Vision+ Alerts - Awaiting UAT screenshots |  |  |  | NA |  |  |  | Sampath | Open | Sampath
9 | Loader broken - this was fixed but now again loader is broken, does not let you proceed further for booking |  |  | Previously fixed issues - Reopened |  | Broken loader | Fixed | Pass | Fixed | Closed
XPRESS CASH - Could not book XC due to loader issue
1 | Cash Limit reduction to 10% from the default cash limit of 28% - vision+ issue. Raised with FDC | Observation Parked, awaiting confirmation to Re-test |  |  | NA |  |  |  | V+ issue- Manish to update | Open | Manish/Siva
2 | Multiple entries in the Booking file.Booking request initiated twice - but reflects 7 times |  | Implementation change at App level. Winjit to come back on date |  | Not Fixed - This is not an issue . Number of times user clicks on button a request will be initiated. We do not have freeze screen implemented anywhere in the app . Loader is cancellable , once it is cancelled new request is initiated |  | Fixed - We have disabled Submit button till response comes for 1 API call Let us know if issue still persists | Pass | Fixed | Closed
| IFSC screen on VAS booking |  |  | Previously fixed issues - Reopened |  | Done' CTA not working | Fixed | Pass | Fixed | Closed
NEW | Other bank dropdown shows RBL bank details and these get populated on selecting | [7 empty] | Reema to come back on the issue- New observation | Open | Business
BALANCE TRANSFER - Error on Booking - Databse Exception
1 | Customer's Account number appended with '000' hence NEFT being Rejected by other Bank | Observation Parked - awaiting confirmation to Re-test |  |  | Fixed | Ok |  |  | Signoff received from Business | Closed
2 | All cases not being recorded in the VAS Booking file. BT booked from front end but case not recorded in VAS Booking file - Case where NEFT Failed, checked from NEFT records |  | 2020-05-29 |  | NA |  |  |  | 1. triple 000" issue resolved(Sapna to run the etl for booking file) App level UAT testing done successfully done 2. Data not get captured in EXAT table v+ issue (Issue highlighted to Pavan & Jinal) | Closed/Open | Sapna/Pavan
3 | NEFT Reject cases part of EMI booking file - Increases Operational Manual work |  | Needs to be operationally handled |  | NA |  |  |  | triple 000" issue- Fixed | Closed/Open | Sapna
4 | Error on Booking - Card not Activated while the card is active |  | Not from App Prespective - check with vision+ team |  | NA |  |  |  | Sampath | Open | Sampath
5 | Other bank credit card field should be masked and re-enter other bank credit card field should be visible - ios issue |  | Already delivered |  | Fixed |  | Fixed | iOS device is unavailable | Fixed( Won’t be able to test the issue in iOS ) | Open | Abhinav
6 | Error on Booking - No record for given card (appears for customer's booking for first time) Needs to be supressed |  | 2020-05-29 |  | Fixed |  | Fixed | Pass | Fixed | Closed
7 | Change in Description for Transpernpay |  |  |  | NA |  |  |  | Transfer N pay verbiage to be corrected Pavan will check in V+ | Open | Vishakha/Pavan
8 | Scroll issue on BT booking page |  |  | Previously fixed issues - Reopened |  |  | Fixed | Pass | Fixed ( Won’t be able to test the issue on iOS,as issue is with ios device) | Open | Abhinav
9 | Database Exception error on booking |  |  | Previously fixed issues - Reopened |  |  | Not Fixed - TBD Sampath; same issue Row - 35 |  | Winjit to fix(suppressed issue) | Open | Winjit
STPL
1 | Solution built only for Transactors | Observation Parked - awaiting confirmation to Re-test | planid reqd in data. 04-Jun |  | NA |  |  |  | 1. UAT testing done for STPL(1 successfull booking done, another scenario app crash issue highlighted to winjit team) 2. Sapna need to check UAT/CUG successful transaction details for overall STPL 3. CUG deployment pending | Closed/Open | Winjit
2 | Incorrect Plan booked at backend - 2 columns need to be added in Plan Master to fetch correct Plan |  | 2020-06-04 |  | NA |  |  |  |  | Closed/Open | Sapna/Sampath
3 | Over limit charged on STPL Account |  |  |  | NA |  |  |  |  | Closed/Open | Sapna/Sampath
4 | Booking file discrepancy - Case appears as failed in booking file, but appears successful in NEFT records |  | 2020-05-29 |  | NA |  |  |  |  | Closed/Open | Sapna/Sampath
5 | Ashi getting updated without bank details |  | 2020-06-04 |  | NA |  |  |  |  | Closed/Open | Sapna/Sampath
6 | ROI % for Plans getting round off in DB - to fix character length for this |  | 2020-05-29 |  | NA |  |  |  |  | Closed/Open | Sapna/Sampath
7 | Error on OTP Page - Database Exception & Invalid Request |  |  |  | NA |  |  |  |  | Closed/Open | Sapna/Sampath
8 | 1. Processing Fee Error on details screen - Previous STPL account is blocked 2. IFSC - not fetching any details per the city and branch |  |  |  | NA |  |  |  |  | Closed/Open | Sapna/Sampath
SNP
1 | Supressing of Debit/Credit entries not relevant to customers | Observation Parked - awaiting confirmation to Re-test | 2020-06-10 | [5 empty] | Winjit to fix | Open | Winjit
UI/UX
1 | Wallet Protection | Since this is not going LIVE - front end 'NEW' tag will have to removed |  |  |  |  | Fixed - Added "Coming Soon" pop up on click of it DO NOT send any notification or offers deeplinking for Wallet Protection | Pass | Insurance not for Go Live | NA | NA
2 | Sign off - Pivot roots observations on recent build | [7 empty] | NA | NA | NA

## Pivot
Count of Status |  | Count of Status
Status | Total | SPOC | Total
Closed | 18 | Abhinav | 3
Closed/Open | 12 | Abhinav/Winjit | 1
Open | 25 | Business | 1
NA | 4 | Manish/Siva | 1
Grand Total | 59 | Manish/Vishakha | 2
|  | NA | 2
|  | Sampath | 4
|  | Sapna | 2
|  | Sapna/Pavan | 1
|  | Sapna/Sampath | 7
|  | Vishakha/Pavan | 1
|  | Winjit | 9
|  | Winjit/Manish/Vishakha | 1
|  | Winjit/Vishakha | 1
|  | (blank) | 23
|  | Grand Total | 59

## UAT Observations
S.No | Observation | BSG comments
1 | Unable to view TAD/MAD on Make Payment screen Credential 8169089997 SAGIR1234A | To be tested on CUG
3 | Get Instant cash on RBL getting error as "We apologize…" on OTP screen after entring OTP
4 | Unable to Switch on Credit card as user keeps getting error "Block Code…" | Sampath to check
5 | Edit Profile : when user clicks on Upload Profile Photo then system keeps on loading | s3 bucket
6 | Location Pop-up keep coming even after clicking on Deny everytime user is re-directed to Dashboard | Winjit to check
7 | No redirection after inviting friend successfully | Winjit to check
8 | Upload Document getting an error "Java.Lang.NullPointer.." | To be tested on CUG
9 | If old pin and new pin is same, error message is "Invalid Credentials" | Winjit to check
10 | e-statement Toggle button is not working properly | Winjit to check
11 | Indisplay Finger print is some time displaying .. It's intermittent issue | Winjit to check
12 | Card Not Present Pop-up | Vishakha
13 | STPL getting an error "No Plans Available…" after entering OTP | Sapna to provide Plan id against UAT cards
14 | Unable to view Reward break detail under Offer & Rewards | As details were not presnt in DB, so the error was reflecting
15 | BT - OTP navigation issue | Vishakha